## 1.Instructions
Instructions on how to fill out the project development table
Annex 1 presents the format of the project development table, which is divided into tab 2. Project development table and tab 3. Contribution to indicators. Below are the instructions for filling in each tab.
Tab 2. This tab is used to complete the PDT with the information indicated below:
  Specific objectives (SO): In column B, include a maximum of 5 SOs. A specific objective is a statement that details the project's objective. A good objective should begin with a verb and meet the SMART criteria: specific, measurable, achievable, result-oriented, and time-bound.
  Expected results (ER): In column C, indicate the ERs for each SO (maximum of 3 per SO).
  Result Performance Indicators (RPI): Measure the extent to which the results have been achieved. To measure the project's progress percentage, the RPI should be expressed in quantitative terms (number, percentage, proportion). The performance indicators may be the same as Phase III result indicators, but there may also be additional indicators. In column D, define a PI (and unit of measure) for each indicator. Include in column E, labeled "target", the value of the PI that you want to achieve at the end of the project. Column F, labeled "indicator result", should not be filled out as part of the PP. It is included in the PDT to track the RPI once the PP is approved. This will later be included in the reports. When submitting your PP, these cells must be zeroed. In column G, define the means of verification for each PI. This is the information that provides evidence of the implementation of activities and determines the methods to be used to collect them.
  Activities (A): In column H, indicate the activities to be carried out to achieve each ER. The activities should refer to specific actions to be carried out and be focused on achieving the expected results. Indicate whether the activities will be carried out in collaboration with other organizations or networks of organizations. In item 10 of section II of this template, you may describe each activity of your project in greater detail.
  In column I, you should indicate, for each activity included, to which Phase III result corresponds to:
    Result 1 of Phase III: “The CMPAs have better conditions for the conservation of their natural resources”,
    Result 2 of Phase III: “Measures implemented for the sustainable use of CMPA natural resources with the participation of the local population,” and
    Result 3 of Phase III: “Strengthened cooperation among key stakeholders for the conservation of the MAR biodiversity.”
  Implementation timeline: In columns J-U labeled "Time Unit," schedule your activities per quarter and year of implementation.
  Products: In column V, include the list of generated products per activity, if applicable. Products are materials produced by the project, such as strategies, manuals, books or articles published or to be published, videos/documentaries, maps, infrastructures, management programs, and online platforms, whose benefit and use will endure beyond the duration of the project. Sometimes, these products may serve as a means of verification, but there are means of verification that are not products, such as meeting minutes, official records, photographs, databases, meeting recordings, payment receipts, survey data, photographic reports, activity reports, geo-referenced locations, among others.
  Activity Performance Indicators (API): Measure the rate at which activities have been implemented. To measure the project´s progress percentage, the API must be expressed in quantitative terms (number, percentage, proportion). Performance indicators can be the same as the Phase III result indicators, but there can also be additional indicators. In column W, define an API (and unit of measurement) for each indicator. Include in column X, labeled "indicator target," the API value you want to achieve at the end of the project. Column Y, labeled "result," should not be filled out as part of the PP. It is included in the PDT to monitor the APIs once the PP is approved. This will later be indicated in the reports. When submitting your PP, these cells should be zeroed. In column Z, define the means of verification for each API, that is, the information that provides evidence of the progress of activities and determines the methods that will be used to collect them.
  Impact indicators (II): They measure long-term changes. The change must be positive and may refer to a constructive behavioral change in people or a direct change in the environment, among others. It is possible that the impacts presented may not be achieved during the course of this project, but it is important to indicate what is expected as a long-term impact. Some of the impact indicators may be the same as the Phase III objective indicators, but there may also be additional indicators. Remember to link the impact indicators (II) in column AA only to the project SOs, not to the activities or ERs. Each SO must have at least one II, but may include more than one II per SO, if necessary. Include in column AB the baseline value of the II at the beginning of the project. Its value can be zero if it is something that has not been done before. Include in column AC the target value of the II you want to achieve at the end of the project. Column AD, labeled "indicator result," should not be filled out in the PP. It is included in the PDT to follow up on the IIs once the PP is approved. This will later be included in the reports. When submitting your PP, these cells should be zeroed.
  Assumptions: Define in column AE the preconditions, if any, that must be in place in order to develop the project. Significant events, conditions, or decisions necessary for long-term sustainability.
  Project´s progress percentage: The AF column should not be completed as part of the PP. It is included in the PDT to monitor the progress of the project once the PP is approved. It will be subsequently included in the reports. The project's progress percentage value is automatically calculated when the information is entered in the columns corresponding to the activity performance indicator. Please do not modify the formula.
Tab 3. This tab is used to indicate the contribution of your project to Phase III indicators. It includes the Phase III Logical Framework: in column A, the objective and the 3 results are presented, and in column B, the objective (3) and result (6) indicators to which your project can contribute. Your project must contribute to the following Phase III indicators:
  Projects under funding line 1: Indicator O1: Area in hectares with better conservation
  Projects under funding line 2: Indicator O2: Area of relevant ecosystems with more sustainable use
  You must also contribute to at least 2 additional indicators of the Phase III Logical Framework, which you can select from the list and mark with an X in Column C.
  For each mandatory and additional selected indicator, you must complete columns D and E indicating your baseline at the beginning of the project and the target indicator value you expect to achieve at the end of your project.

## 2. Project Development Table
Project name:
Proponent:
Country:
Coastal Marine Protected Area(s):
| To be filled out by the proponent | [30 empty] | Comments by the proponent organization | Comments by MAR Fund
PROJECT OBJECTIVE:
| Specific Objective(s) (SO) | Expected results (ER) | Result Performance Indicators (RPI) (define units of measure) |  |  |  | Activities (A) | Phase III result to which it corresponds | Time units (quarters) | [11 empty] | Products | Activity Performance Indicator (API) (define units of measure) |  |  |  | Impact Indicator (II) |  |  |  | Assumptions | Project's Progress %
[9 empty] | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
|  |  | Indicator and unit of measure | Target | Indicator result | Means of verification |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | Indicator and unit of measure | Indicator target | Result | Means of verification | Indicator and unit of measure | Baseline | Indicator target | Indicator result
Follow the instruction and then hide this row | Include a maximum of 5 specific objectives (SO). An SO is a statement that details the project's objective. A good objective should begin with a verb and meet the SMART criteria: specific, measurable, achievable, result-oriented, and time-bound. | Indicate the ERs for each SO (maximum of 3 per SO). | It measures the extent to which results have been achieved. To measure the project's progress %, the RPI should be expressed in quantitative terms (number, percentage, proportion). The performance indicators may be the same as Phase III result indicators, but there may also be additional indicators. | Include the RPI value you want to achieve at the end of the project. | This column should not be filled out as part of the PP. It is included in the PDT to track the RPI once the PP is approved. This will later be included in the reports. When submitting your PP, these cells must be zeroed. | This is the information that provides evidence of the implementation of activities and determines the methods to be used to collect them. | Indicate the activities to be carried out to achieve each ER. The activities should refer to specific actions to be carried out and be focused on achieving the expected results. Indicate whether the activities will be carried out in collaboration with other organizations or networks of organizations. | Indicate which Phase III result each activity included corresponds to. Result 1 of Phase III. The CMPAs have better conditions for the conservation of their natural resources. Result 2 of Phase III. Measures implemented for the sustainable use of CMPA natural resources with the participation of the local population. Result 3 of Phase III. Strengthened cooperation among key stakeholders for the conservation of the MAR biodiversity. | Year 1 1: Schedule your activities per quarter and year of implementation | Include the list of generated products per activity, if applicable. Products are materials produced by the project, such as strategies, manuals, books or articles published or to be published, videos/documentaries, maps, infrastructure, management programs, and online platforms, whose benefit and use will remain beyond the duration of the project. Sometimes, these outputs may serve as a means of verification, but there are means of verification that are not products, such as meeting minutes, official records, photographs, databases, meeting recordings, payment receipts, survey data, photographic reports, activity reports, geo-referenced locations, among others. | It measures the rate at which activities have been implemented. To measure the project's progress %, the API must be expressed in quantitative terms (number, percentage, proportion). Performance indicators can be the same as the Phase III result indicators, but there can also be additional indicators. | Include the API value you want to achieve at the end of the project. | This column should not be filled out as part of the PP. It is included in the PDT to monitor APIs once the PP is approved. This will later be indicated in the reports. When submitting your PP, these cells should be zeroed. | It is the information that provides evidence of the progress of activities and determines the methods that will be used to collect them. | It measures long-term change. The change must be positive and may refer to a constructive behavioral change in people or a direct change in the environment, among others. It is possible that the impacts presented may not be achieved during the course of this project, but it is important to indicate what is expected as a long-term impact. Some of the impact indicators may be the same as Phase III objective indicators, but there may also be additional indicators. Remember to link the impact indicators (II) only to the project SOs, not to the activities or ERs. Each SO must have at least one II, but may include more than one II per SO, if necessary. | Include the baseline value of the II at the beginning of the project. Its value can be zero if it is something that has not been done before. | Include the II target value you want to achieve at the end of the project. | This column should not be filled out as part of the PP. It is included in the PDT to follow up on the IIs once the PP is approved. This will later be included in the reports. When submitting your PP, these cells should be zeroed. | Refers to the preconditions, if any, that must be in place in order to develop the project. Significant events, conditions or decisions necessary for long-term sustainability. | This column should not be completed as part of the PP. It is included in the PDT to monitor the progress of the project once the PP is approved. It will be subsequently included in the reports. The project's progress percentage value is automatically calculated when the information is entered in the columns corresponding to the Activity Performance Indicator. Please do not modify the formula.
Example: Remove before sending the proposal | SO 1. Co-manager provides, by the end of 2022, information about the ecology and importance of Cayos Cochinos to visitors, to contribute to its conservation | ER 1.1 A descriptive marine trail that informs visitors is established | Number of people who visited the descriptive trail | 200 |  | Visitor registration | A 1.1.1 Design, exchange workshops between CMPAs, and construction of the descriptive trail and open route, where visitor entry and exit surveys are conducted. | Result 1 and Result 3 of Phase III | [12 empty] | Descriptive trail of Cayos Cochinos | Km of built descriptive trail | 150 | 0 | Photographic record of the completed construction of the road | # of informed visitors committed to take at least one action or change one habit or behavior to protect Cayos Cochinos | 0 | 50 | 0 | There is visitation at Cayos Cochinos | 0 | bar: Year 1 1 to Year 1 3
Example: Remove before sending the proposal | SO 2. Increase, by the end of 2022, the mangrove area in the Manglares de Nichupté Natural Protected Area with the participation of the community | ER 2.1 Residents of the "La Pila" community have the knowledge and participate in mangrove restoration work | Number of people trained | 30 |  | Course completion certificates | A 2.1.1 Setup and training of community groups | Result 1 of Phase III | [12 empty] | Training kit for participatory mangrove restoration | # of trained people | 30 | 0 | Course completion certificates | restored ha | 300 | 305 | 0 | The community is interested in participating and getting trained | 0 | bar: Year 1 3 to Year 2 5
|  | ER 2.2 The mangrove area in the Manglares de Nichupté NPA is increased | % increase of restored ha | 10% |  | Aerial photographs of restored areas | A 2.2.1 Seedling collection | Result 1 of Phase III | [12 empty] | N/A | # of collected seedlings | 50 | 0 | Report on field activities |  |  |  |  | There is a good source of seedlings in the area for restoration | 0 | bar: Year 2 6
[7 empty] | A 2.2.2 Construction of mangrove platforms and replanting of mangrove seedlings | Result 1 of Phase III | [12 empty] | N/A | # of replanted seedlings | 800 | 0 | Report on field activities | [5 empty] | 0 | bar: Year 2 7 to Year 3 9
|  | ER 2.3 Seedlings survive and begin to change the landscape | % survival | 70% |  | Monitoring databases | A 2.3.1 Implementation of permanent plots for mangrove monitoring | Result 1 of Phase III | [12 empty] | N/A | # monitoring events | 1 | 1 | Monitoring report/database | Increased biodiversity (# of species found) | 15 | 27 | 0 | Restoration is conducted at the end of the hurricane season so that seedlings can have a longer stabilization period | 100 | bar: Year 3 12
| SO1 | ER 1.1 |  |  |  |  | A 1.1.1 | [15 empty] | 20 | 10 |  | I1. |  |  |  |  | 50
[7 empty] | A 1.1.2 | [23 empty] | #DIV/0!
|  | ER 1.2 |  |  |  |  | A 1.2.1 | [23 empty] | #DIV/0!
[7 empty] | A 1.2.2 | [23 empty] | #DIV/0!
| SO2 | ER 2.1 |  |  |  |  | A 2.1.1 | [18 empty] | I2. |  |  |  |  | #DIV/0!
[7 empty] | A 2.1.2 | [23 empty] | #DIV/0!
|  | ER 2.2 |  |  |  |  | A 2.2.1 | [23 empty] | #DIV/0!
[7 empty] | A 2.2.2 | [23 empty] | #DIV/0!
| SO3 | ER 3.1 |  |  |  |  | A 3.1.1 | [15 empty] | 20 | 10 |  | I3. |  |  |  |  | 50
[7 empty] | A 3.1.2 | [23 empty] | #DIV/0!
|  | ER 3.2 |  |  |  |  | A 3.2.1 | [23 empty] | #DIV/0!
[7 empty] | A 3.2.2 | [23 empty] | #DIV/0!
| SO4 | ER 4.1 |  |  |  |  | A 4.1.1 | [15 empty] | 20 | 10 |  | I4. |  |  |  |  | 50
[7 empty] | A 4.1.2 | [23 empty] | #DIV/0!

## 3.Contribution to indicators
Logical Framework for the project "Conservation of Maritime Resources in Central America III" (Phase III)
Objective and Results of Phase III | Phase III Indicator | Mark the Phase III indicators to which your project contributes | Baseline of your project | Indicator target for your project
Objective: Conservation and sustainable use of natural resources in and between targeted coastal marine protected areas (CMPAs) of the Mesoamerican Reef System (MAR). | Indicator O.1: Area in hectares with better conservation (Mandatory)
Indicator O.2: Area of relevant ecosystems with more sustainable use (Mandatory)
Indicator O.3: Number of initiatives that support the adaptation of populations vulnerable to climate change.
Result 1 of Phase III: The CMPAs have better conditions for the conservation of their natural resources. | Indicator R 1.1: Number of CMPAs implementing best conservation practices
Indicator R 1.2: Number of people involved in the management of CMPAs with enhanced capabilities
Indicator R 1.3: Number of selected CMPAs with at least 75% of management effectiveness (Mandatory)
Result 2 of Phase III: Measures implemented for the sustainable use of the natural resources of CMPAs with the participation of the local population. | Indicator R 2.1: Number of natural resource use plans developed with the local population under implementation
Indicator R 2.2: Number of people directly supported by the project who benefit from the sustainable use of natural resources
Result 3 of Phase III: Strengthened cooperation among key stakeholders for biodiversity conservation in the MAR . | Indicator R 3.2: Number of joint initiatives between CMPAs implemented within the framework of the project